## Project overview
GitHub link:	https://github.com/3dquake/secret_of_evermore_clone					Title	Status		Time spent on project
				Character #1: Human	fixme: companion ai		Wed	6 hours	6
				Character #2: Dog	fixme: companion ai		Thu	8 hours	8
				Inventory	Done FIXME: items		Fri	9 hours	9
Priority	Name	Type	Misc.			Implementation	Status	Time				Enemies w/ AI	Done FIXME: ai stuck when player dies		Sat
(Important > 3)			Abstract	Mono					Camera	Done		Sun
0	GameManager	Logic		X		Creates other managers, holds all static info, holds inventory, creates visual prefabs based on the info from other managers	Done	3 hours	3					Total	23
0	CharacterManager	Logic				List of chars (or two distinct members), list of enemies, selected character	Done	2 hour	2			Extras
1	UIManager	Logic				Responsible for initializing, opening, keeping track of panels	Done	2 hours	2			Ability to cast spells
1	EvermorePanel	Logic	X	X		Defines method for panels (init, refresh ...)	Done	30 minutes				NPC stores
2	Character	Logic				Hold all info about related to characters (name hp mp wp stats level att def ...)	Done	30 minutes	1			NPC teachers
2	Item	Logic	X			Contains enum ItemType & member, and amount of that item		1 hour	1			Switching to different era
2	Armor	Logic				Inherits from 'Item', increases character defence, ArmorType enum & member		5 minutes				Part of a level which requires a dog	Done
2	Weapon	Logic	X			Inherits from 'Item', holds common members		10 minutes				Different enemies
2	Sword / Bow / Staff	Logic				Inherits from 'Weapon', contains weapon specific behaviour, increase ATT stat of Character (excluding staff)
1	Inventory	Logic				Contains list of items		4 hours	4
1	InventoryPanel	Presentation				Inherits from 'EvermorePanel', opens with pressing button on HUD, shows characters stats and bonus from items	Done	1 hour	1
2	VisualCharacter	Presentation		X		Member of Character (link from UI to logic), single model (cube/capsule)	Done	2 hours	2
2	HUD	Presentation		X		Gets information from managers and updates hud accordingly	Done	1 hour	1
2	CharacterPanel	Presentation				Inherits from EvermorePanel and opens with pressing a button on HUD	Done	1 hour	1
1	Level	Scene				Complete gameplay from Corner A to Corner B
3	Main menu	Scene				Can load a level and quit a game. And options too	Done	15 minutes
	AI Behaviour	Logic				Attacking, moving, reacting; Inherits from StateMachine	Done	3 hours	3
	Companion Behaviour	Logic				Inherits from AI Behaviour
	VisualItem	Presentation		X		Represents the Item and it's descentants in the game world	Done	30 minutes
	StateMachine	Logic	X			Base class for Finite State Machines	Done	30 minutes	1
	CameraController	Logic				Class for managing cameras; Inherits from StateMachine	Done	2 hours	2
	State	Logic	X			Base class for use in Finite State Machines	Done	30 minutes	1
				25