## Project overview
GitHub link:	https://github.com/3dquake/secret_of_evermore_clone

Priority	Name	Type	Misc.			Implementation	Status	Time
(Important > 3)			Abstract	Mono
0	GameManager	Data		X		Creates other managers, holds all static info, holds inventory, creates visual prefabs based on the info from other managers		2 hours
0	CharacterManager	Data				List of chars (or two distinct members), list of enemies, selected character		1 hour
1	UIManager	Data				Responsible for initializing, opening, keeping track of panels	Done	2 hours
1	EvermorePanel	Data	X	X		Defines method for panels (init, refresh ...)	Done	30 minutes
2	Character	Data				Hold all info about related to characters (name hp mp wp stats level att def ...)		30 minutes
2	Item	Data	X			Contains enum ItemType & member, and amount of that item		10 minutes
2	Armor	Data				Inherits from 'Item', increases character defence, ArmorType enum & member		10 minutes
2	Weapon	Data	X			Inherits from 'Item', holds common members		0
2	Sword / Bow / Staff	Data				Inherits from 'Weapon', contains weapon specific behaviour, increase ATT stat of Character (excluding staff)
1	Inventory	Data				Contains list of items
1	InventoryPanel	Presentation				Inherits from 'EvermorePanel', opens with pressing button on HUD, shows characters stats and bonus from items
2	VisualCharacter	Presentation		X		Member of Character (link from UI to logic), single model (cube/capsule)	Done
2	HUD	Presentation		X		Gets information from managers and updates hud accordingly
2	CharacterPanel	Presentation				Inherits from evermorepanel opens with pressing a button on HUD	Done	1 hour
	Level	Scene				Complete gameplay from Corner A to Corner B
	Main menu	Scene				Can load a level and quit a game	Done	15 minutes

## To-do
Title	Status		Time spent on project
Working level	WIP		Wed	6 hours
Character #1	WIP		Thu	4 hours
Character #2			Fri
Inventory	WIP		Sat
Enemies w/ AI			Sun
Camera	Done
Extras
Ability to cast spells
NPC stores
NPC teachers
Switching to different era
Part of a level which requires a dog
Different enemies